## November Release
ID | Beschreibung | Arbeitspakte | Zuständigkeit SVAG | Aktion | BMW Status | SVAG Statu
1 | Design Phase | System Design Update of the latest version of the GUARDAEN Implementation Concept Deliverable: GUARDEAN Implementation Concept | Ruben | wurde erstellt und an Kunden verschickt. Abnahme BMW erforderlich. | offen | erledigt
| Implementierung | Beistellung erforderlich (Konfigurationstabellen von der Produktion) | Mikhail | bei Patrick Alberts angefragt. | offen | offen
2 | Implementation & Test Phase | Implementation of the changes - Enhancement of the scripting service CheckRestrictedPolicyRulesC-62 Deliverable: - Updated scripting service | Mikhail | Für die Implementierung wird die Version mit Race Service verwendet - Service CheckRestrictedPolicyRules wurde in Anlehnung an das Design Konzept hier implementiert: http://svag-1182703d:7001/control_center/ bei frClient und frClient_cbu_on_stab | offen | in Bearbeitung
|  | Pre-Delivery-Test-Cases - Preparation and execution of 3 pre-delivery test cases to review the changes Deliverable: An excel sheet based on an ALM template sheet for the import in ALM | Mikhail | Pre-delivery tests werden erstellt und an Marie geliefert. 'Abstimmung mit Marie am 11.09.2018. Im Anschluss können die Tests erstellt, durchgeführt und in AML hochgeladen werden. | offen | offen
3 | Deliveries and Packages | Preparation of the final delivery and packages - The final delivery will be provided as a project Tarball delivery (based on the Tarball structure as provided in the RiskSuite 6.3 migration delivery). The installation (incl. rollback) will be done automatically (with less manual steps) Deliverable: Installation packages (incl. installation and rollback scripts) | Mikhail | Abstimmung TARBALL Mikhail mit Henning am 12.09.2018. Im Anschluss kann der Projekt - TARBALL beigestellt werden. Tarball wird im Anschluss an die Fertigstellung der Implementierung von Philipp an BMW geliefert (Komm. Montag) | offen | offen
4 | Support & Go-Live | Support for UAT - Analysis and Support during 4 weeks UAT phase. - Any additional support has to be ordered separately As it is a support task no deliverable available |  | tbd | offen | offen
|  | Go Live Support for Production - This includes an on call support for the go-live on production, based on the assumption that go live takes place during the week in the evening hours. |  |  | offen | offen